## 📋 Overview
AI Telemetry POC — Implementation Plan
Custom Metrics & Usage Tracking on Azure · 2-Week POC · Under $200/month
OBJECTIVE
Build a working proof of concept that demonstrates end-to-end AI request observability on Azure. A synthetic data generator simulates real LLM application traffic. Every request produces OTel metrics, Kafka usage events, and structured logs. A live Grafana dashboard shows cost, latency, tokens, and errors updating every 30 seconds. The same pipeline connects to a real LLM application by changing one config value.
Phase | Duration | Starts | Goal | Key Output | Acceptance Criteria | Status
Phase 0 — Prerequisites | 2 days | Before W1 | All Azure services provisioned, env vars confirmed, dev environment ready | 7 Azure resources running · all connectivity tests pass | Every checklist item in Phase 0 confirmed before week 1 starts
Week 1 — Generator + Kafka + Metrics + Dashboard Start | 5 days | Day 1 | Generator + Kafka pipeline + OTel metrics flowing · Grafana data sources connected · KPI panels live | runner.py producing events · Event Hubs shows messages · Azure Monitor shows 5 metrics · 6 KPI panels live | 10 requests → 10 START/END pairs → 10 OTel metric increments · validation passes · KPI stat panels show non-zero values
Week 2 — Dashboard + Deploy + Hand-over | 5 days | Day 6 | All 14 panels live · alerts configured · generator in Container App · Bicep IaC · documentation delivered | Dashboard JSON exported · Container deployed · Bicep deploys cleanly · README + runbook complete | Dashboard refreshes every 30s · alert email received · Real HTTP request appears in dashboard · Bicep teardown + redeploy < 25 min
✅ What this POC proves to stakeholders
✓ Synthetic LLM traffic at 50–200 requests/minute across 4 models and 7 client teams
✓ Every request emits Kafka START + END events to Azure Event Hubs — linked by event_id
✓ Every request increments 5 OTel instruments in Azure Monitor Prometheus
✓ Grafana dashboard: 14 panels — request volume, latency p50/p95/p99, cost by team, model mix, tokens, errors
✓ Alert fires within 2 minutes when error rate exceeds 5% — email delivered, annotation on chart
✓ Full pipeline restartable in under 5 minutes from cold start
✓ Single config change connects pipeline to real LLM traffic — no downstream changes needed
💰 Azure cost estimate (dev/test tiers)
Service | Tier | Estimated Cost/mo
Azure Event Hubs | Standard 1 TU | $11/mo
Azure Cache for Redis | C1 Standard | $55/mo
Cosmos DB for MongoDB | Serverless | $8/mo
Azure Monitor Prometheus | Pay-per-GB | $15/mo
Azure Managed Grafana | Standard tier | $65/mo — largest cost
Azure Container Apps | Consumption plan | $5/mo
Azure Key Vault | Standard | $5/mo
Azure Container Registry | Basic tier | $5/mo
TOTAL | Dev/test tiers | ~$169/mo

## 🔧 Phase 0 — Prerequisites
Phase 0 — Prerequisites & Setup
All items must be provisioned and verified BEFORE week 1 day 1. Do not start Phase 1 until every acceptance criteria row is checked.
Azure Resource / Action | Tier / Config | Owner | Lead Time | Acceptance Criteria | Status
🏗 Azure Resources to Provision
Azure Resource Group | rg-ai-telemetry-poc · choose region | DevOps | 30 min | az group show --name rg-ai-telemetry-poc returns success
Azure Event Hubs Namespace + Hub | Standard tier · 1 TU · Hub: ai-telemetry-events · 6 partitions · 7-day retention | DevOps / Infra | 1 day | Python confluent-kafka producer sends test message without error · visible in Portal Data Explorer
Azure Cache for Redis | C1 Standard (1 GB) · TLS enabled · port 6380 | DevOps / Infra | 1 day | redis-py ping() returns PONG from deployment network
Azure Cosmos DB for MongoDB API | Serverless tier · DB: telemetry · Collection: model-metadata | DevOps / Data Eng | 1 day | motor client lists collections without error · model-metadata contains 4 documents
Cosmos DB — model-metadata seeded | 4 docs: claude-haiku-3-5, claude-sonnet-4-5, gpt-4o, claude-opus-4-6 · each with cost_per_1m_input_tokens, cost_per_1m_output_tokens, cost_per_1m_cache_read_tokens | Data Eng | 2 hrs | ⚠ CRITICAL: if not seeded, request_cost metric emits zero for entire POC
Azure Monitor Workspace | amw-telemetry-poc · note data collection endpoint URL and Prometheus remote write URL | SRE | 30 min | Workspace appears in Azure Monitor · endpoint URL available
Azure Managed Grafana | Standard tier · linked to Monitor workspace during creation | SRE | 1 day | Grafana UI accessible · Azure Monitor data source shows as connected
Azure Key Vault | Standard tier · 6 secrets: eventhub-connection-string, redis-connection-string, cosmos-connection-string, monitor-workspace-id, otlp-endpoint, grafana-url | Security / DevOps | 2 hrs | All 6 secrets created · delivery team has Key Vault Secrets User role
Azure Container Registry | Basic tier · admin user enabled | DevOps | 30 min | az acr login succeeds · docker push works
💻 Local Development Environment
Python 3.11 + virtual env | python3.11 -m venv .venv · pip install -r requirements.txt | Delivery Team | 1 hr | python --version shows 3.11.x · all packages install without error
Azure CLI + logged in | az --version ≥ 2.55 · az login completed | Delivery Team | 30 min | az account show returns correct subscription
Docker Desktop | Docker Desktop ≥ 4.x · docker ps works | Delivery Team | 30 min | docker run hello-world succeeds
Repository structure created | generator/ · gateway_simulator/ · dashboards/ · infra/ · .env.example | Delivery Team | 2 hrs | All folders exist · .env.example documents every required variable
🔑 Environment Variables — All Required Before Day 1
EVENTHUB_NAMESPACE | your-namespace.servicebus.windows.net | DevOps | From Portal | Value present in .env · Python os.environ access works
EVENTHUB_CONNECTION_STRING | Endpoint=sb://... (from Shared Access Policies) | DevOps | From Portal | confluent-kafka producer connects using this value
EVENTHUB_NAME | ai-telemetry-events | DevOps | Fixed value | Matches Event Hub name in Portal
OTEL_EXPORTER_OTLP_ENDPOINT | https://ingest.monitor.azure.com/... (from Monitor workspace) | SRE | From Portal | OTel exporter connects without 401/403 error
OTEL_SERVICE_NAME | ai-telemetry-poc | Delivery Team | Fixed value | Appears as service.name label in Azure Monitor
COSMOS_CONNECTION_STRING | mongodb://account:key@account.mongo.cosmos.azure.com:10255/... | DevOps | From Portal | motor client connects and reads model-metadata collection
REDIS_URL | rediss://:accesskey@name.redis.cache.windows.net:6380 | DevOps | From Portal | redis-py PING returns PONG · SSL handshake succeeds
✅ Phase 0 Gate — Do Not Proceed to Week 1 Until All Pass
Connectivity gate | Run: python phase0_check.py | Delivery Team | Day -1 | All 7 checks print PASS: Event Hubs · Redis · Cosmos · OTel · Grafana · Key Vault · ACR

## 📅 Week 1 — Generator
Week 1 — Generator + Kafka Pipeline + OTel Metrics + Dashboard Start
Goal: synthetic LLM events flowing to Azure Event Hubs and Azure Monitor by mid-week · Grafana data sources connected and 6 KPI stat panels live by end of week 1
Day | Task | Implementation Detail | Acceptance Criteria | Est. Hours | Status
Day 1 — Build the Synthetic Data Generator
D1 | Write synthetic_generator.py | SyntheticLLMGenerator class with MODELS dict (4 models, weighted), CLIENTS list (7 teams, weighted), OPERATIONS list. Implement: generate_batch(n, error_window), traffic_multiplier() for day/night shape, calculate_cost() from token counts and model pricing | Generate 1000 events · model distribution within 5% of targets (Haiku 61% / Sonnet 24% / GPT-4o 10% / Opus 5%) · cost calculation verified manually for one event | 4 hrs
D1 | Unit test the generator | Write test_generator.py: test model weights over 1000 events, test cost calculation accuracy, test error rate (0.8% normal, ~8% error_window=True), test all required fields present in every event | All tests pass · no missing fields · error rate within 0.3% of target | 2 hrs
Day 2 — Build the Kafka Publisher
D2 | Write kafka_publisher.py | UsageEventPublisher class connecting to Event Hubs via Kafka protocol (SASL_SSL, port 9093). Implement publish_start() and publish_end() methods. Use event['request_id'] as event_id on both. Partition by client_name key. Delivery callback logs errors | Producer connects without error · one START and one END visible in Azure Portal Event Hubs Data Explorer · event_id matches between pair | 3 hrs
D2 | Implement resilient publish with retry | On delivery callback error: retry 2× with linear backoff (sleep 0.1s × attempt). On permanent failure: log at ERROR level with full payload. Mirror production gateway behaviour exactly | Force a connection error · verify retry fires 2× · verify ERROR log contains full payload | 2 hrs
Day 3 — OTel Metrics Pipeline + Continuous Runner
D3 | Write otel_metrics.py + record_request_metrics() | setup_otel() initialises MeterProvider with OTLPMetricExporter and PeriodicExportingMetricReader (30s interval). Register 5 instruments: ai_gateway_request_count (counter), ai_gateway_request_duration (histogram), ai_gateway_request_token (counter), ai_gateway_request_cost (counter), ai_gateway_exception_count (counter). Implement record_request_metrics() — single function called after each event, adds all 5 instrument recordings with correct attributes. Token counter called 3× per event (prompt, completion, cache_read). exception_count fires only on status=error. | After 100 events: Azure Monitor Metrics Explorer shows ai_gateway_request_count · metric has model_name and client_name dimensions · histogram shows count + sum + buckets · cost total matches manual sum | 4 hrs
D3 | Write runner.py + structured logging | Main loop: generate batch sized by traffic_multiplier() × random.gauss(8,2). For each event: publish_start → sleep(latency_ms/1000) → publish_end → record_request_metrics → logging.info('request_simulated', extra={request_id, model_name, client_name, latency_ms, cost_usd, status}). Error window: 3% chance per minute of entering 90–180s error window. SIGTERM handler for clean shutdown. logging.warning on error window start/end. logging.error with full payload on Kafka failure. | Runner runs 30 min without crash · Event Hubs message count increases steadily · log output parseable as JSON · all required fields present · error window triggers approximately once per 30 min | 4 hrs
Day 4 — Week 1 Validation + Configure Grafana Data Sources
D4 | Run validation/check_week1.py | (1) consume 500 events from Event Hubs and verify every START has matching END within 60s. (2) model distribution within 5% of targets. (3) cost accuracy: recalculate from tokens, compare to recorded cost_usd. (4) no negative token counts. (5) total_tokens = prompt + completion + cache_read. | All 5 validation checks print PASS · zero orphaned START events · cost accuracy within 0.1% | 3 hrs
D4 | Connect Grafana data sources + verify PromQL queries | Grafana → Connections → Data sources → Add Prometheus (URL: https://prometheusEndpoint.monitor.azure.com/workspaces/<id>/api/v1, Managed Identity auth) AND Azure Monitor data source. Run 5 test queries: (1) sum(ai_gateway_request_count_total) (2) sum by (model_name) (3) histogram_quantile(0.95, ...) (4) sum(ai_gateway_request_cost_total) (5) sum by (client_name). Document PromQL strings for each panel. | Both data sources show Connected · all 5 test queries return non-zero values · model_name shows 4 models · client_name shows 7 teams | 5 hrs
Day 5 — KPI Stat Panels (6 panels) + Week 1 Review
D5 | Panel 1–3: Total requests, Avg latency p50, Total cost | Stat panels. Reduce: Last. Colour mode: Background. (1) sum(increase(ai_gateway_request_count_total[24h])) (2) histogram_quantile(0.50, sum(rate(ai_gateway_request_duration_bucket[5m])) by (le)) unit: ms (3) sum(increase(ai_gateway_request_cost_total[24h])) unit: currency USD. | 3 panels show correct values · latency p50 between 620ms (Haiku) and 3800ms (Opus) weighted avg · cost matches manual estimate | 3 hrs
D5 | Panel 4–6: Error rate, Total tokens, Cost per request + Week 1 review | (4) error rate = sum(rate{status=error}[5m]) / sum(rate[5m]) — thresholds: green <1%, yellow <5%, red ≥5%. (5) sum(increase(ai_gateway_request_token_total[24h])) unit: short. (6) sum(rate cost[5m]) / sum(rate count[5m]). Week 1 review: walk through Event Hubs Data Explorer + Azure Monitor metrics + 6 live KPI panels with stakeholders. | Error rate panel turns yellow during normal traffic (0.8%) · tokens shows ~124M for 24h · cost per request ~$0.0005–$0.002 · screenshots committed to repo | 4 hrs

## 📊 Week 2 — Dashboard
Week 2 — Dashboard Finish + Containerise + Deploy + IaC + Hand-over
Goal: all 14 panels live · alerts firing · generator in Azure Container App · Bicep IaC · documentation delivered · sign-off complete
Day | Task | Implementation Detail | Acceptance Criteria | Est. Hours | Status
Day 6 — Time Series Charts (Row 2) + Cost by Client Bar
D6 | Request volume by model (area chart) | Time series panel. 4 queries — one per model: sum(rate(ai_gateway_request_count_total{model_name='claude-haiku-3-5'}[5m])) * 60 (req/min). Repeat for Sonnet, GPT-4o, Opus. Legend: {{model_name}}. Colours: Haiku=teal, Sonnet=purple, GPT-4o=blue, Opus=coral. Fill below line: 15% opacity. Stack: off. | Chart shows 4 coloured area series · Haiku area is visibly largest (~61%) · traffic rises during simulated peak hours | 3 hrs
D6 | Latency p50/p95/p99 distribution chart | Time series panel. 3 queries: histogram_quantile(0.50/0.95/0.99, sum(rate(ai_gateway_request_duration_bucket[5m])) by (le)). Y axis unit: milliseconds. p99 = red dashed, p95 = amber solid, p50 = green solid. Thresholds: 4000ms warning, 8000ms critical. | 3 lines clearly separated · p99 (dashed red) highest · p50 lowest · during error window p99 spikes visibly | 2 hrs
D6 | Cost by client team (horizontal bar) | Bar chart panel. Horizontal orientation. Query: sum(increase(ai_gateway_request_cost_total[24h])) by (client_name). Sort: descending. Colour: gradient teal to blue. X axis unit: USD. | healthcare-portal shows as highest bar · 7 bars total · bars proportional to client weights in generator | 2 hrs
Day 7 — Donut/Tokens/Exception Panels + Configure Alerts + Dashboard Export
D7 | Model routing donut + token stacked bar + exception chart | Donut: sum(increase(ai_gateway_request_count_total[24h])) by (model_name) — verify ~61/24/10/5 split. Token stacked bar: 3 queries by token_type for prompt/completion/cache_read stacked. Exception bar: sum(increase(ai_gateway_exception_count_total[1m])) — colour red. | Donut shows correct model mix ±5% · token bar shows prompt > completion > cache_read · exception bar spikes during error window | 3 hrs
D7 | Alert rules (2) + dashboard JSON export | Alert 1 — High Error Rate: query = error rate PromQL, IS ABOVE 0.05, pending 2 min, email notification, runbook URL annotation. Alert 2 — High p95 Latency: IS ABOVE 8000ms, pending 3 min. Force error_window_probability=1.0 in runner to verify alert fires within 2 min. Dashboard → Share → Export → save to dashboards/grafana_dashboard.json. Commit to repo. | Both alerts fire on demand · email received · annotation appears on exception panel · dashboard JSON committed · all 14 panels show non-zero data | 5 hrs
Day 8 — Containerise + Push to ACR + Deploy to Container Apps
D8 | Write Dockerfile + build + push to Azure Container Registry | FROM python:3.11-slim. COPY requirements.txt, pip install --no-cache-dir. COPY . . ENV PYTHONUNBUFFERED=1. CMD python runner.py. requirements.txt pinned: confluent-kafka==2.3.0, opentelemetry-api==1.40.0, opentelemetry-sdk==1.40.0, otlp-exporter-grpc==1.40.0, motor==3.3.1, redis==5.0.1, azure-identity==1.15.0, azure-keyvault-secrets==4.7.0. Build: az acr build --registry <acr-name> --image ai-telemetry-generator:v1 ./generator. Verify in ACR repository. | docker build succeeds with zero errors · docker run locally produces request_simulated log lines · image visible in ACR · image size under 500 MB | 3 hrs
D8 | Deploy generator as Azure Container App | az containerapp env create --name ai-telemetry-env --resource-group rg-ai-telemetry-poc. Associate with Log Analytics workspace. az containerapp create --name ai-telemetry-generator --image <acr>.azurecr.io/ai-telemetry-generator:v1 --min-replicas 1 --max-replicas 1. Set all env vars as Key Vault secret references. Assign system-managed identity with Key Vault Secrets User and Event Hubs Data Sender roles. | Container App shows Running · az containerapp logs show --follow shows request_simulated lines · Grafana dashboard continues updating with no local process running · no hardcoded secrets in code or image | 4 hrs
Day 9 — FastAPI Gateway Simulator + Bicep IaC Start
D9 | Build FastAPI gateway simulator (real HTTP path) | Write gateway_simulator/main.py: FastAPI app with POST /v1/chat/completions endpoint. Accepts OpenAI-compatible request body. Calls generator.generate_batch(1)[0] to simulate one event. Sets client_name from X-Client-Name header, model_name from request body. Calls publish_start → asyncio.sleep(latency/1000) → publish_end → record_request_metrics. Returns OpenAI-compatible response JSON. Test with `from openai import OpenAI; client = OpenAI(base_url='http://localhost:8000/v1', api_key='test')`. | curl -X POST /v1/chat/completions returns valid OpenAI JSON · request appears in Grafana dashboard within 30s · event_id links START and END in Event Hubs · OpenAI Python client works with no code changes | 4 hrs
D9 | Begin Bicep IaC — infra/main.bicep | Bicep template creating all resources in order: resource group · Event Hubs namespace + hub · Cosmos DB + database seeding · Redis Cache · Monitor workspace · Managed Grafana linked to workspace · Key Vault + all secrets · Container App environment + app · Role assignments for managed identity (Event Hubs Data Sender, Key Vault Secrets User, Monitor Metrics Publisher). Day 9 goal: scaffolded template + first 4 resources deploying. | az deployment group validate passes · resource group + Event Hubs + Cosmos + Redis deploy without errors in test resource group | 3 hrs
Day 10 — Bicep Finish + Teardown Test + Final Validation + Hand-over
D10 | Finish Bicep + teardown + redeploy test | Complete Bicep template with Monitor workspace, Grafana, Key Vault + secrets, Container App env + app, and all role assignments. Test full lifecycle: az group delete --name rg-ai-telemetry-poc --yes. Wait for complete deletion. Re-run: az group create && az deployment group create --template-file infra/main.bicep. Time the redeployment. | az deployment group create completes without errors · all resources visible in Portal · Container App starts automatically · full teardown + redeploy < 25 min · Grafana dashboard shows data within 5 min of completion | 5 hrs
D10 | Final validation + documentation package + sign-off | Run validation/final_check.py — 9 checks: (1) Container App running. (2) Event Hubs >100 msg/min. (3) all 5 OTel metrics updating. (4) Dashboard refreshing every 30s. (5) Model distribution ±5% of targets. (6) Cost per request within 10% of expected. (7) event_id pairing 100%. (8) Force error window → alert fires → email received. (9) Real HTTP request via /v1/chat/completions appears in dashboard. Deliver: README.md, docs/architecture.md, docs/extending-to-production.md, docs/runbook.md. Off-board delivery team. Get sign-off. | All 9 checks print PASS · all 4 docs in repo · README instructions reproduce environment in < 30 min by someone unfamiliar with project · sign-off document signed by client engineering lead | 5 hrs

## 📅 Gantt Timeline
POC Implementation Gantt — Phase 0 + 2 Weeks + 12 Working Days
Green = active days · milestone diamonds shown at end of each phase
|  | Phase 0 — Prerequisites |  | Week 1 — Generator + Kafka |  |  |  |  | Week 2 — Grafana Dashboard
Task | Hrs | P0-1 | P0-2 | W1-D1 | W1-D2 | W1-D3 | W1-D4 | W1-D5 | W2-D1 | W2-D2 | W2-D3 | W2-D4 | W2-D5
Azure resource provisioning | 6h | █ | █
Local dev environment setup | 4h | █ | █
Env vars + connectivity tests | 2h |  | █
Write synthetic_generator.py | 4h |  |  | █
Unit test generator | 2h |  |  | █
Write kafka_publisher.py | 3h |  |  |  | █
Resilient publish + retry | 2h |  |  |  | █
otel_metrics + record_request_metrics() | 4h |  |  |  |  | █
runner.py + structured logging | 4h |  |  |  |  | █
W1 validation suite (check_week1.py) | 3h | [5 empty] | █
Grafana data sources + PromQL verify | 5h | [5 empty] | █
KPI stat panels 1–3 (requests, latency, cost) | 3h | [6 empty] | █
KPI stat panels 4–6 + W1 review | 4h | [6 empty] | █
Time series — volume + latency | 5h | [7 empty] | █
Cost by client (horizontal bar) | 2h | [7 empty] | █
Donut + token stack + exception bar | 3h | [8 empty] | █
Alert rules + dashboard JSON export | 5h | [8 empty] | █
Dockerfile + push to ACR | 3h | [9 empty] | █
Deploy to Container Apps | 4h | [9 empty] | █
FastAPI gateway simulator | 4h | [10 empty] | █
Bicep IaC scaffold + first resources | 3h | [10 empty] | █
Bicep finish + teardown + redeploy test | 5h | [11 empty] | █
Final validation + docs + sign-off | 5h | [11 empty] | █
◆ Milestones |  |  | ◆ |  |  |  |  | ◆ |  |  |  |  | ◆

## ✅ Acceptance Criteria
POC Acceptance Criteria & Sign-off Checklist
Every row must be checked before the POC is considered complete. Status column: Not Started → In Progress → Pass → Fail
Phase | Acceptance Criteria | How to Verify | Priority | Status
🔧 Phase 0 — Prerequisites
Phase 0 | All 7 Azure resources show as Provisioned in Portal | az resource list --resource-group rg-ai-telemetry-poc ¦ jq length == 7+ | Critical
Phase 0 | Python confluent-kafka producer connects to Event Hubs and sends test message without error | Run: python validation/test_eventhubs.py — prints PASS | Critical
Phase 0 | redis-py PING returns PONG from gateway network | Run: python -c "import redis; r=redis.from_url(REDIS_URL); print(r.ping())" | Critical
Phase 0 | motor MongoDB client connects and reads model-metadata — 4 documents present with pricing fields | Run: python validation/test_cosmos.py — prints all 4 model names with costs | Critical
Phase 0 | Grafana UI accessible and Azure Monitor data source shows Connected | Open Grafana URL in browser · Connections → Data Sources shows green tick | Critical
📡 Week 1 — Data Generator & Pipeline
Week 1 | Model distribution within 5% of targets over 1000 events (Haiku ~61%, Sonnet ~24%, GPT-4o ~10%, Opus ~5%) | Run: python validation/check_distribution.py 1000 — prints per-model % and PASS/FAIL | High
Week 1 | Every START event has a matching END event within 60 seconds (event_id correlation 100%) | Run: python validation/check_event_pairs.py — zero orphaned STARTs after 60s | Critical
Week 1 | Cost accuracy: recalculated cost from token counts matches cost_usd within 0.1% | Run: python validation/check_cost_accuracy.py — all events within threshold | High
Week 1 | Azure Monitor shows all 5 OTel metrics updating: request_count, request_duration, request_token, request_cost, exception_count | Azure Monitor → Metrics Explorer → select each metric — non-zero values visible | Critical
Week 1 | runner.py runs continuously for 30 minutes without crash or exception | python runner.py & sleep 1800 — check process still running, no ERROR in logs | High
Week 1 | Error window triggers approximately once per 30 minutes and error rate spikes to ~8% | Watch logs over 60 min — at least one error_window_started log entry visible | Medium
📊 Week 2 — Dashboard + Deploy + Hand-over
Week 2 | All 14 dashboard panels show non-zero data and update every 30 seconds | Watch dashboard for 2 minutes — all panels show values, values change on refresh | Critical
Week 2 | Model routing donut shows Haiku ~61% / Sonnet ~24% / GPT-4o ~10% / Opus ~5% within ±5% | Read percentages from donut chart — compare to generator weights | High
Week 2 | Cost by client team: healthcare-portal is highest bar, all 7 teams visible | Horizontal bar chart shows 7 bars, healthcare-portal at top | High
Week 2 | Latency p50/p95/p99 lines clearly separated — p99 highest, p50 lowest, units in milliseconds | Read values from time series chart — p99 should be 4–6× higher than p50 | High
Week 2 | Error rate panel turns yellow (>1%) when error window is active | Force error window · watch error rate panel · confirm colour changes to yellow within 2 min | High
Week 2 | Alert rule fires within 2 minutes of error rate exceeding 5% and email is received | Set error_window_probability=1.0 · wait 2 min · check email inbox · check Grafana alert state | Critical
Week 2 | Alert annotation appears on exception panel chart when alert fires | During alert fire — exception panel shows vertical annotation line with label | Medium
Week 2 | Dashboard JSON exported to dashboards/grafana_dashboard.json and committed to repository | File exists in repo · import JSON into a fresh Grafana instance — dashboard recreates correctly | High
Week 2 | Container image builds with zero errors and size under 500 MB | docker build · docker images ¦ grep ai-telemetry-generator — note size | High
Week 2 | Generator runs as Azure Container App with no local process — dashboard continues updating | Stop all local processes · watch dashboard for 2 minutes — still updating from Container App | Critical
Week 2 | Real HTTP request to /v1/chat/completions appears in Grafana dashboard within 30 seconds | curl -X POST http://gateway-url/v1/chat/completions -d '{"model":"claude-haiku-3-5","messages":[...]}' · watch dashboard for request_count increment | Critical
Week 2 | Bicep deployment completes without errors in a clean resource group | az group create + az deployment group create — exit code 0, all resources visible in Portal | High
Week 2 | Full teardown + redeploy completes in under 25 minutes and POC is fully operational | az group delete + timed redeploy — record time · run validation/final_check.py after | High
Week 2 | README.md instructions followed by a new person produce a working environment in under 30 minutes | Pair with someone unfamiliar with the project — they follow README, time the process | High
Week 2 | All 4 documentation files complete: README, architecture, extending-to-production, runbook | File exists in repo · each doc reviewed by at least one stakeholder | High
Week 2 | Sign-off document signed by client engineering lead | Physical or digital signature on sign-off_poc.md | Critical